## Slide 1: Post-Award Timeline for ACC Contractors
Christina Quast
Operations Administrator

## Slide 2: Readiness
March - Initial Kick-Off Readiness/Transition Meeting
April – Provider Utilization file (network)
April – Initial Readiness Assessment Tool (RAT) submission due
  6 total submissions
*Dates subject to change

## Slide 3: Readiness (cont.)
Monthly Update Meetings with Exec and DHCM Management
  Present on a set agenda
June – ACC Contractor Websites in place
*Dates subject to change

## Slide 4: Member Transition
April – Calls begin with all plans to discuss Data Elements File (DEF), and what supplemental files may be needed
  Ongoing until final formats agreed upon
June – Initial member assignment
June – Member letters with choice options
July – 30-day member choice period
  Member choice portal
*Dates subject to change

## Slide 5: Member Transition (cont.)
August – Final member assignment
August – Begin transmitting DEF and Supplemental files (test files in July)
  Calls between transmission dates to discuss any issues
  5 total files
  AHCCCS the intermediary for files
*Dates subject to change

## Slide 6: Questions?

## Slide 7: Thank You.