## Instructions
Complete the Pricing Schedule AHCCCS shall pay the awarded contractor based on the total annual amount in 12 equal monthly increments. Provide the annual cost of requested AI Call Center Integration, including Design, Development & Implementation (DDI) and Maintenance & Operations (M&O). AHCCCS anticipates a six (6) to twelve (12)-month DDI, and a four (4)-year M&O period, with a total contract duration of five (5) years. Enter DDI pricing for contracts years 1, and pricing for M&O years 1.5-5. Provide pricing for the Solution Deliverables and associated Milestone payments. Refer to the AI Call Center Integration deliverables in the Requirements Response Matrix for detailed description of each deliverable. Pricing shall be inclusive of all costs associated with the delivery of the services and includes staff time, travel, mileage, insurance, and administrative cost. No additional fees will be paid by AHCCCS. Provide the staffing rates for extra services (for example, rates for modification hours or change requests).

## Summary
Task Order # YH26-0031
AI Call Center Integration
ATTACHMENT B: PRICING PROPOSAL WORKSHEET
OFFEROR NAME: |  |  | Accenture LLP
Total System Cost Summaries
This will be the Total Cost Summaries from each of the Tabs in this spreadsheet
Description | One Time Costs | Year 1 Costs | Year 2 Costs | Year 3 Costs | Year 4 Costs | Year 5 Costs
Solution Costs | 0 | 5802115 | 1354349 | 829894 | 878458 | 935066
| 0 | 5802115 | 1354349 | 829894 | 878458 | 935066
5-year Cost of Ownership: | 9799882

## Solution Price
Task Order # YH26-0031
AI Call Center Integration
SOLUTION PRICING
**refer to the timeline in the Task Order for a detailed description of the anticipated activities included in each line item**
Provide a line item for all costs. | Total One Time Cost
Description |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
Planning & Requirements | 0 | 750590 | 0 | 0 | 0 | 0 | 750590
Design & Architecture | 0 | 909806 | 0 | 0 | 0 | 0 | 909806
Build & Configuration | 0 | 1455690 | 0 | 0 | 0 | 0 | 1455690
Testing & Validation | 0 | 1023532 | 0 | 0 | 0 | 0 | 1023532
Pilot & Training | 0 | 401960 | 0 | 0 | 0 | 0 | 401960
Full Rollout & Go-Live | 0 | 363922 | 0 | 0 | 0 | 0 | 363922
Reporting | 0 | 45490 | 0 | 0 | 0 | 0 | 45490
Maintenance & Operations | 0 | 851125 | 1354349 | 829894 | 878458 | 935066 | 4848892
Subscription & Licensing (if applicable)** | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hosting (if applicable)** | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost: | 0 | 5802115 | 1354349 | 829894 | 878458 | 935066 | 9799882
Solution Costs shall include all travel. Use the following assumptions for estimating travel:
*For Requirements Section of the Scope of Work: 1-2 trips for each State
*For Development: No travel should be assumed
*For Testing the System: 1 trip should be assumed for each State
*For Implementation of the System: 1-2 trips should be assumed for each State
*For Training: 1-2 trips should be assumed for each State
*The duration should be assumed to be 2-3 days per trip for each State
**Please note that the Software and License costs should include licensing costs for each component of the Solution, which will be hosted in the AHCCCS Azure environment. AHCCCS will host the Solution and retain ownership of the licensing for each component.

## Solution Deliverables
Task Order # YH26-0031
AI Call Center Integration
SOLUTION DELIVERABLES
**Refer to AI Call Center Integration Deliverables for detailed description of each item**
Milestone | Base Price | Recurring Cost (if any) | # of Hours | Proposed Timeline
1. Planning and Requirements
a. Weekly Project Planning/Status Meetings | 75058.995 |  | 270 | Month 1
b. Develop milestone schedule. (weekly, monthly and quarterly) | 150118 |  | 545 | Month 1
c. Requirements Traceability Matrix | 225177 |  | 810 | Month 1
d. Project Management Plan | 187648 |  | 675 | Month 1
e. Communications Management Plan | 112588 |  | 405 | Month 1
2. Design and Architecture
a. Technical Architecture Detailed Description (DTAP) | 272942 |  | 985 | Month 2
b. Requirements Traceability Matrix | 181961 |  | 660 | Month 2
c. Business Continuity, Cyber Incident Response, & Disaster Recovery Plan (BC/CIR/DR) | 90980.6 |  | 325 | Month 1
d. Business Design / System Design Document (BD/SDD) | 363922.4 |  | 1310 | Month 2
3. Build and Configuration
a. System Change Plan | 225177 |  | 810 | Month 1
b. Data Management Plan | 300236 |  | 1085 | Month 2
c. Environmental Monitoring Plan | 150118 |  | 540 | Month 2
d. System Maintenance Support Plan (SysMSP) | 225177 |  | 810 | Month 2
e. System Security & Privacy Plan (SSPP) | 225177 |  | 810 | Month 1
f. Release Management Plan | 375295 |  | 1355 | Month 2
4. Testing and Validation
a. Test Management Plan (TMP) | 255883 |  | 922 | Month 1
b. Validation of test reporting | 204706 |  | 740 | Month 4
c. Error reporting and remediation planning for test stages | 307060 |  | 1105 | Month 3
d. Testing acceptance signoff | 102353 |  | 368 | Month 5
e. Quality Management Plan (QMP) | 153530 |  | 555 | Month 1
5. Pilot and Training
a. User Training Plan | 120588 |  | 434 | Month 2
b. Training Curriculum | 281372 |  | 1015 | Month 4
6. Full RollOut and Go-Live
a. Implementation/Roll out plan to include dashboard reporting. | 76424 |  | 275 | Month 3
b. Validation of production reports | 43670 |  | 155 | Month 5
c. Ongoing error reporting | 32753 |  | 120 | Month 5
d. Performance Management Plan | 32753 |  | 120 | Month 2
e. Continuance of Operations Program (COOP) | 32753 |  | 120 | Month 4
7. Optimization and Support
a. Post implementation plan for AHCCCS, Genesys and ServiceNow | 24747 |  | 88 | Month 4
b. Post implementation documentation delivery | 26202 |  | 96 | Month 5
c. Post implementation support/maintenance plan | 36392 |  | 132 | Month 5
d. Error reporting and remediation planning | 23292 |  | 84 | Month 5
e. Transition Plan | 34936 |  | 124 | Month 1

## Staffing Rates
Instructions: Please use the cells shaded in yellow to list all position titles and rates associated with your response. Enter the Hourly Billable Rate per Positions for each Position Title. The Hourly Billable Rate should factor in all costs including applicable purchase, delivery, tax, services, safety, license, travel, per diem, Respondent's staff training, facilities, and other such items necessary to complete all deliverables. The Respondent may include additional roles to accurately represent the various classifications and grades of its personnel.
Table 1: Position Titles and Rates
Position Title | Description | HOURLY Billable Rate Per Position
Example - Analyst | Organizes collected data; analyzes data; assist in developing reports. | 65
Engagement Lead | Leads client engagement, manages AI-driven solutions in call centers, and aligns stakeholders. | 425
Conversation Designer / Build Lead | Develops AI user flows, aligning interactions with goals and enhancing voice/chat channels. | 425
Security SME | Defines security for AI, ensures data privacy compliance, and mitigates project risks. | 425
Project Manager / Delivery Lead | Oversees project delivery, coordinates teams, and drives timely deployment of solutions. | 385
Solution Architect | Develops scalable AI architectures, aligns solutions with goals, and ensures system compatibility. | 355
Technology Specialist 1 | Supports project execution, performs DDI activities, and uploads delivery timelines. | 255
Technology Specialist 2 / Test Lead | Supports project execution, performs DDI activities, and uploads delivery timelines. | 295
Technology Specialist 3 | Supports project execution, performs DDI activities, and uploads delivery timelines. | 325
Support Analyst | Offers operational support, monitors performance, handles escalations, and maintains operations. | 210
Program Director | Oversees and responsible for all engagements within the program for the Client. | 548
Business Process Improvement Manager | Drives AI automation, redesigns workflows, and improves call center KPIs and processes. | 433
Business Process Sr. Consultant | Leads AI-driven optimization, supports change management, and ensures best practices. | 360
Business Process Analyst | Analyzes workflows, identifies AI gaps, and documents insights for transformation efforts. | 277
Program Analyst | Tracks AI impact, supports change management, and analyzes metrics for business improvements. | 210
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0