## Instructions
Complete the Pricing Schedule AHCCCS shall pay the awarded contractor based on the total annual amount in 12 equal monthly increments. Provide the annual cost of requested AI Call Center Integration, including Design, Development & Implementation (DDI) and Maintenance & Operations (M&O). AHCCCS anticipates a six (6) to twelve (12)-month DDI, and a four (4)-year M&O period, with a total contract duration of five (5) years. Enter DDI pricing for contracts years 1, and pricing for M&O years 1.5-5. Provide pricing for the Solution Deliverables and associated Milestone payments. Refer to the AI Call Center Integration deliverables in the Requirements Response Matrix for detailed description of each deliverable. Pricing shall be inclusive of all costs associated with the delivery of the services and includes staff time, travel, mileage, insurance, and administrative cost. No additional fees will be paid by AHCCCS. Provide the staffing rates for extra services (for example, rates for modification hours or change requests).

## Summary
Task Order # YH26-0031
AI Call Center Integration
ATTACHMENT B: PRICING PROPOSAL WORKSHEET
OFFEROR NAME: |  |  | Deloitte Consulting LLP
Total System Cost Summaries
This will be the Total Cost Summaries from each of the Tabs in this spreadsheet
Description | One Time Costs | Year 1 Costs | Year 2 Costs | Year 3 Costs | Year 4 Costs | Year 5 Costs
Solution Costs | 0 | 3401017.3525 | 1425000 | 1353000 | 1290000 | 1250000
| 0 | 3401017.3525 | 1425000 | 1353000 | 1290000 | 1250000
5-year Cost of Ownership: | 8719017.3525

## Solution Price
Task Order # YH26-0031
AI Call Center Integration
SOLUTION PRICING
**refer to the timeline in the Task Order for a detailed description of the anticipated activities included in each line item**
Provide a line item for all costs. | Total One Time Cost
Description |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
Planning & Requirements |  | 171322.4727 | 0 | 0 | 0 | 0 | 171322.4727
Design & Architecture |  | 353158.7822 | 0 | 0 | 0 | 0 | 353158.7822
Build & Configuration |  | 1735126.7006 | 0 | 0 | 0 | 0 | 1735126.7006
Testing & Validation |  | 156693.6 | 0 | 0 | 0 | 0 | 156693.6
Pilot & Training |  | 193964.832 | 0 | 0 | 0 | 0 | 193964.832
Full Rollout & Go-Live |  | 493464.525 | 0 | 0 | 0 | 0 | 493464.525
Reporting |  | 297286.44 | 0 | 0 | 0 | 0 | 297286.44
Maintenance & Operations |  |  | 1425000 | 1353000 | 1290000 | 1250000 | 5318000
Subscription & Licensing (if applicable)** |  | 0 | 0 | 0 | 0 | 0 | 0
Hosting (if applicable)** |  | 0 | 0 | 0 | 0 | 0 | 0
Total Cost: | 0 | 3401017.3525 | 1425000 | 1353000 | 1290000 | 1250000 | 8719017.3525
Solution Costs shall include all travel. Use the following assumptions for estimating travel:
*For Requirements Section of the Scope of Work: 1-2 trips for each State
*For Development: No travel should be assumed
*For Testing the System: 1 trip should be assumed for each State
*For Implementation of the System: 1-2 trips should be assumed for each State
*For Training: 1-2 trips should be assumed for each State
*The duration should be assumed to be 2-3 days per trip for each State
**Please note that the Software and License costs should include licensing costs for each component of the Solution, which will be hosted in the AHCCCS Azure environment. AHCCCS will host the Solution and retain ownership of the licensing for each component.

## Solution Deliverables
Task Order # YH26-0031
AI Call Center Integration
SOLUTION DELIVERABLES
**Refer to AI Call Center Integration Deliverables for detailed description of each item**
Milestone | Base Price | Recurring Cost (if any) | # of Hours | Proposed Timeline
1. Planning and Requirements
a. Weekly Project Planning/Status Meetings | 42830.6182 | N/A | 122 | Ongoing Through Months 1 - 6
b. Develop milestone schedule. (weekly, monthly and quarterly) | N/A | N/A | N/A | Completed as Part of Project Management Plan
c. Requirements Traceability Matrix | 42830.6182 | Updates Included in M&O | 122 | Thirty (30) business days post Contract Start Date
d. Project Management Plan | 42830.6182 | N/A | 122 | Thirty (30) business days post Contract Start Date
e. Communications Management Plan | 42830.6182 | Updates Included in M&O | 122 | Thirty (30) business days post Contract Start Date
2. Design and Architecture
a. Technical Architecture Detailed Description (DTAP) | 176579.3911 | Updates Included in M&O | 604 | Six (6) months post Contract Start
b. Requirements Traceability Matrix | 44144.8478 | Updates Included in M&O | 151 | Thirty (30) business days post Contract Start
c. Business Continuity, Cyber Incident Response, & Disaster Recovery Plan (BC/CIR/DR) | 44144.8478 | Updates Included in M&O | 151 | Thirty (30) business days post Contract Start
d. Business Design / System Design Document (BD/SDD) | 88289.6956 | Updates Included in M&O | 302 | Sixty (60) business days post Contract Start
3. Build and Configuration
a. System Change Plan | 289187.7834 | Updates Included in M&O | 1263.3333 | Three (3) months post Contract Start
b. Data Management Plan | 289187.7834 | Updates Included in M&O | 1263.3333 | Two (2) months post Contract Start
c. Environmental Monitoring Plan | 289187.7834 | Updates Included in M&O | 1263.3333 | Three (3) months post Contract Start
d. System Maintenance Support Plan (SysMSP) | 289187.7834 | Updates Included in M&O | 1263.3333 | Forty (40) business days post Contract Start
e. System Security & Privacy Plan (SSPP) | 289187.7834 | Updates Included in M&O | 1263.3333 | Thirty (30) business days post Contract Start
f. Release Management Plan | 289187.7834 | Updates Included in M&O | 1263.3333 | Four (4) months post Contract Start
4. Testing and Validation
a. Test Management Plan (TMP) | 52231.2 | Updates Included in M&O | 320 | Two (2) months post Contract Start
b. Validation of test reporting | N/A | N/A | N/A | Completed as Part of Testing Acceptance Signoff
c. Error reporting and remediation planning for test stages | N/A | N/A | N/A | Completed as Part of Test Management Plan
d. Testing acceptance signoff | 52231.2 | N/A | 320 | Six (6) months post Contract Start
e. Quality Management Plan (QMP) | 52231.2 | Updates Included in M&O | 320 | Thirty (30) business days post Contract Start
5. Pilot and Training
a. User Training Plan | 96982.416 | N/A | 480 | Sixty (60) days from Contract Start
b. Training Curriculum | 96982.416 | N/A | 480 | Five (5) months post Contract Start
6. Full RollOut and Go-Live
a. Implementation/Roll out plan to include dashboard reporting. | 164488.175 | Updates Included in M&O | 632 | Four (4) months post Contract Start
b. Validation of production reports | N/A | N/A | N/A | Completed as Part of Implementation Plan
c. Ongoing error reporting | N/A | N/A | N/A | Included as part of Implementation Plan
d. Performance Management Plan | 164488.175 | Updates Included in M&O | 632 | Sixty (60) business days post Contract Execution
e. Continuance of Operations Program (COOP) | 164488.175 | Updates Included in M&O | 632 | Five (5) months post Contract Start
7. Optimization and Support
a. Post implementation plan for AHCCCS, Genesys and ServiceNow | N/A | N/A | N/A | Included as part of Post Implementation Maintenance and Operations
b. Post implementation documentation delivery | N/A | N/A | N/A | Included as part of Post Implementation Maintenance and Operations
c. Post implementation support/maintenance plan | N/A | N/A | N/A | Included as part of Post Implementation Maintenance and Operations
d. Error reporting and remediation planning | N/A | N/A | N/A | Included as part of Post Implementation Maintenance and Operations
e. Transition Plan | N/A | N/A | N/A | Included as part of Post Implementation Maintenance and Operations

## Staffing Rates
Instructions: Please use the cells shaded in yellow to list all position titles and rates associated with your response. Enter the Hourly Billable Rate per Positions for each Position Title. The Hourly Billable Rate should factor in all costs including applicable purchase, delivery, tax, services, safety, license, travel, per diem, Respondent's staff training, facilities, and other such items necessary to complete all deliverables. The Respondent may include additional roles to accurately represent the various classifications and grades of its personnel.
Table 1: Position Titles and Rates
Position Title | Description | HOURLY Billable Rate Per Position
Example - Analyst | Organizes collected data; analyzes data; assist in developing reports. | 65
Subject Matter Expert (SME) | Provides deep domain expertise across business and tech | 280
Project Manager | Oversees planning, coordination, and delivery of AI solutions | 266
Project Management Team Member | Assists in PM tasks; tracking deliverables, support communications | 190
Support Staff (If Applicable) | Provides operational and administrative assistance; documentation | 180
AI Lead | Guides the design and integration of AI-driven solutions | 278
AI Analyst | Supports AI solutions, optimizations, and automation | 175
Data Analyst | Extracts, interprets, and provides reports and insights | 190
Sr. CCaaS and CRM Architect | Designs the overarching architecture and integration strategy | 325
Sr. CCaaS and CRM Engineer | Leads the architecture, customization, and deployment of AI solutions | 275
CCaaS and CRM Engineer | Designs and executes testing, validation, and integration | 195
CCaaS and CRM Testing Engineer | Designs and executes testing, validation, and integration | 165
Sr. Security Architect Senior | Develops and enforces security frameworks, controls, and guardrails | 275
Security Architect | Supports security recommedations and implementation tasks | 195
Training / OCM Lead | Oversees OCM and the development of training content and delivery | 289
CSR Trainer | Designs and conducts training sessions and course content | 165
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0