## Instructions
Complete the Pricing Schedule AHCCCS shall pay the awarded contractor based on the total annual amount in 12 equal monthly increments. Provide the annual cost of requested AI Call Center Integration, including Design, Development & Implementation (DDI) and Maintenance & Operations (M&O). AHCCCS anticipates a six (6) to twelve (12)-month DDI, and a four (4)-year M&O period, with a total contract duration of five (5) years. Enter DDI pricing for contracts years 1, and pricing for M&O years 1.5-5. Provide pricing for the Solution Deliverables and associated Milestone payments. Refer to the AI Call Center Integration deliverables in the Requirements Response Matrix for detailed description of each deliverable. Pricing shall be inclusive of all costs associated with the delivery of the services and includes staff time, travel, mileage, insurance, and administrative cost. No additional fees will be paid by AHCCCS. Provide the staffing rates for extra services (for example, rates for modification hours or change requests).

## Summary
Task Order # YH26-0031
AI Call Center Integration
ATTACHMENT B: PRICING PROPOSAL WORKSHEET
OFFEROR NAME: |  |  | EY
Total System Cost Summaries
This will be the Total Cost Summaries from each of the Tabs in this spreadsheet
Description | One Time Costs | Year 1 Costs | Year 2 Costs | Year 3 Costs | Year 4 Costs | Year 5 Costs
Solution Costs | 0 | 4094365.8 | 765223.04 | 733148.8 | 705083.84 | 685037.44
| 0 | 4094365.8 | 765223.04 | 733148.8 | 705083.84 | 685037.44
5-year Cost of Ownership: | 6982858.92

## Solution Price
Task Order # YH26-0031
AI Call Center Integration
SOLUTION PRICING
**refer to the timeline in the Task Order for a detailed description of the anticipated activities included in each line item**
Provide a line item for all costs. | Total One Time Cost
Description |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
Planning & Requirements | 0 | 81887.32 | 0 | 0 | 0 | 0 | 81887.32
Design & Architecture | 0 | 1105478.76 | 0 | 0 | 0 | 0 | 1105478.76
Build & Configuration | 0 | 1842464.61 | 0 | 0 | 0 | 0 | 1842464.61
Testing & Validation | 0 | 409436.58 | 0 | 0 | 0 | 0 | 409436.58
Pilot & Training | 0 | 204718.29 | 0 | 0 | 0 | 0 | 204718.29
Full Rollout & Go-Live | 0 | 286605.61 | 0 | 0 | 0 | 0 | 286605.61
Reporting | 0 | 163774.63 | 0 | 0 | 0 | 0 | 163774.63
Maintenance & Operations | 0 | 0 | 765223.04 | 733148.8 | 705083.84 | 685037.44 | 2888493.12
Subscription & Licensing (if applicable)** | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hosting (if applicable)** | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost: | 0 | 4094365.8 | 765223.04 | 733148.8 | 705083.84 | 685037.44 | 6982858.92
Solution Costs shall include all travel. Use the following assumptions for estimating travel:
*For Requirements Section of the Scope of Work: 1-2 trips for each State
*For Development: No travel should be assumed
*For Testing the System: 1 trip should be assumed for each State
*For Implementation of the System: 1-2 trips should be assumed for each State
*For Training: 1-2 trips should be assumed for each State
*The duration should be assumed to be 2-3 days per trip for each State
**Please note that the Software and License costs should include licensing costs for each component of the Solution, which will be hosted in the AHCCCS Azure environment. AHCCCS will host the Solution and retain ownership of the licensing for each component.

## Solution Deliverables
Task Order # YH26-0031
AI Call Center Integration
SOLUTION DELIVERABLES
**Refer to AI Call Center Integration Deliverables for detailed description of each item**
Milestone | Base Price | Recurring Cost (if any) | # of Hours | Proposed Timeline
1. Planning and Requirements | 81887.32 |  | 397
a. Weekly Project Planning/Status Meetings | 32754.93 | 2729.5775 | 159 | Est. ongoing (Apr-Jan)
b. Develop milestone schedule. (weekly, monthly and quarterly) | 8188.74 |  | 40 | Est. April 2026
c. Requirements Traceability Matrix | 16377.46 |  | 79 | Est. April 2026
d. Project Management Plan | 16377.46 |  | 79 | Est. April 2026
e. Communications Management Plan | 8188.73 |  | 40 | Est. April 2026
2. Design and Architecture | 1105478.76 |  | 5357
a. Technical Architecture Detailed Description (DTAP) | 331643.63 |  | 1607 | Est. May 2026
b. Requirements Traceability Matrix | 221095.75 |  | 1071 | Est. May 2026
c. Business Continuity, Cyber Incident Response, & Disaster Recovery Plan (BC/CIR/DR) | 110547.88 |  | 536 | Est. June 2026
d. Business Design / System Design Document (BD/SDD) | 442191.5 |  | 2143 | Est. May 2026
3. Build and Configuration | 1842464.61 |  | 8927
a. System Change Plan | 460616.15 |  | 2232 | Est. Oct 2026
b. Data Management Plan | 368492.92 |  | 1785 | Est. Oct 2026
c. Environmental Monitoring Plan | 184246.46 |  | 893 | Est. Oct 2026
d. System Maintenance Support Plan (SysMSP) | 184246.46 |  | 893 | Est. Oct 2026
e. System Security & Privacy Plan (SSPP) | 184246.46 |  | 893 | Est. Oct 2026
f. Release Management Plan | 460616.16 |  | 2231 | Est. Oct 2026
4. Testing and Validation | 409436.58 |  | 1984
a. Test Management Plan (TMP) | 143302.8 |  | 694 | Est. Nov 2026
b. Validation of test reporting | 102359.14 |  | 496 | Est. Nov 2026
c. Error reporting and remediation planning for test stages | 53226.76 |  | 259 | Est. Nov 2026
d. Testing acceptance signoff | 40943.66 |  | 198 | Est. Nov 2026
e. Quality Management Plan (QMP) | 69604.22 |  | 337 | Est. Nov 2026
5. Pilot and Training | 204718.29 |  | 992
a. User Training Plan | 81887.32 |  | 397 | Est. Oct 2026
b. Training Curriculum | 122830.97 |  | 595 | Est. Nov 2026
6. Full RollOut and Go-Live | 286605.61 |  | 1389
a. Implementation/Roll out plan to include dashboard reporting. | 71651.4 |  | 347 | Est. Dec 2026
b. Validation of production reports | 42990.85 |  | 208 | Est. Dec 2026
c. Ongoing error reporting | 28660.56 |  | 139 | Est. Dec 2026
d. Performance Management Plan | 57321.12 |  | 278 | Est. Dec 2026
e. Continuance of Operations Program (COOP) | 85981.68 |  | 417 | Est. Dec 2026
7. Optimization and Support | 163774.63 |  | 794
a. Post implementation plan for AHCCCS, Genesys and ServiceNow | 24566.19 |  | 119 | Est. Dec 2026
b. Post implementation documentation delivery | 65509.85 |  | 318 | Est. Dec 2026
c. Post implementation support/maintenance plan | 16377.47 |  | 79 | Est. Dec 2026
d. Error reporting and remediation planning | 24566.19 |  | 119 | Est. Dec 2026
e. Transition Plan | 32754.93 |  | 159 | Est. Dec 2026

## Staffing Rates
Instructions: Please use the cells shaded in yellow to list all position titles and rates associated with your response. Enter the Hourly Billable Rate per Positions for each Position Title. The Hourly Billable Rate should factor in all costs including applicable purchase, delivery, tax, services, safety, license, travel, per diem, Respondent's staff training, facilities, and other such items necessary to complete all deliverables. The Respondent may include additional roles to accurately represent the various classifications and grades of its personnel.
Table 1: Position Titles and Rates
Position Title | Description | [6 empty] | HOURLY Billable Rate Per Position
Example - Analyst | Organizes collected data; analyzes data; assist in developing reports. | [6 empty] | 65
Engagement Partner | Responsible for overall project oversight, strategy and direction of the project. | Responsible for planning, organizing, and directing the completion of the project. | Responsible for planning, organizing, and directing the completion of the project. | Responsible for planning, organizing, and directing the completion of the project. | Responsible for planning, organizing, and directing the completion of the project. | Responsible for planning, organizing, and directing the completion of the project. | Responsible for planning, organizing, and directing the completion of the project. | 400
Program Manager | Responsible for planning, organizing, and directing the completion of the project. | Responsible for planning, organizing, and directing the completion of the project. | Responsible for planning, organizing, and directing the completion of the project. | Responsible for planning, organizing, and directing the completion of the project. | Responsible for planning, organizing, and directing the completion of the project. | Responsible for planning, organizing, and directing the completion of the project. | Responsible for planning, organizing, and directing the completion of the project. | 350
Subject Matter Resource | Senior advisor to provide direction and advisory services for their relative experiences | Senior advisor to provide direction and advisory services for their relative experiences | Senior advisor to provide direction and advisory services for their relative experiences | Senior advisor to provide direction and advisory services for their relative experiences | Senior advisor to provide direction and advisory services for their relative experiences | Senior advisor to provide direction and advisory services for their relative experiences | Senior advisor to provide direction and advisory services for their relative experiences | 375
Operations Manager | Responsible for overseeing and managing all day-to-day activities to ensure successful operations. | Responsible for overseeing and managing all day-to-day activities to ensure successful operations. | Responsible for overseeing and managing all day-to-day activities to ensure successful operations. | Responsible for overseeing and managing all day-to-day activities to ensure successful operations. | Responsible for overseeing and managing all day-to-day activities to ensure successful operations. | Responsible for overseeing and managing all day-to-day activities to ensure successful operations. | Responsible for overseeing and managing all day-to-day activities to ensure successful operations. | 255
Scrum Master | Facilitates and guides a software development product owner, team, and organization through iterations. Organizes and facilitates meetings, including preparing, moderating, and post processing. Helps with product release planning and enforces deadlines. | Facilitates and guides a software development product owner, team, and organization through iterations. Organizes and facilitates meetings, including preparing, moderating, and post processing. Helps with product release planning and enforces deadlines. | Facilitates and guides a software development product owner, team, and organization through iterations. Organizes and facilitates meetings, including preparing, moderating, and post processing. Helps with product release planning and enforces deadlines. | Facilitates and guides a software development product owner, team, and organization through iterations. Organizes and facilitates meetings, including preparing, moderating, and post processing. Helps with product release planning and enforces deadlines. | Facilitates and guides a software development product owner, team, and organization through iterations. Organizes and facilitates meetings, including preparing, moderating, and post processing. Helps with product release planning and enforces deadlines. | Facilitates and guides a software development product owner, team, and organization through iterations. Organizes and facilitates meetings, including preparing, moderating, and post processing. Helps with product release planning and enforces deadlines. | Facilitates and guides a software development product owner, team, and organization through iterations. Organizes and facilitates meetings, including preparing, moderating, and post processing. Helps with product release planning and enforces deadlines. | 260
Cyber Architect Lead | Leads the development, implementation, and maintenance of cybersecurity infrastructure and policies; Responsible for analyzing security risks, designing secure systems, and ensuring compliance with relevant regulations and standards | Leads the development, implementation, and maintenance of cybersecurity infrastructure and policies; Responsible for analyzing security risks, designing secure systems, and ensuring compliance with relevant regulations and standards | Leads the development, implementation, and maintenance of cybersecurity infrastructure and policies; Responsible for analyzing security risks, designing secure systems, and ensuring compliance with relevant regulations and standards | Leads the development, implementation, and maintenance of cybersecurity infrastructure and policies; Responsible for analyzing security risks, designing secure systems, and ensuring compliance with relevant regulations and standards | Leads the development, implementation, and maintenance of cybersecurity infrastructure and policies; Responsible for analyzing security risks, designing secure systems, and ensuring compliance with relevant regulations and standards | Leads the development, implementation, and maintenance of cybersecurity infrastructure and policies; Responsible for analyzing security risks, designing secure systems, and ensuring compliance with relevant regulations and standards | Leads the development, implementation, and maintenance of cybersecurity infrastructure and policies; Responsible for analyzing security risks, designing secure systems, and ensuring compliance with relevant regulations and standards | 255
Senior Cyber Architect | Senior Level; Responsible for development, implementation and maintenance of cybersecurity infrastructure; Plans, tests, implements, and maintains security solutions, and ensure compliance with relevant policies and regulations. | Senior Level; Responsible for development, implementation and maintenance of cybersecurity infrastructure; Plans, tests, implements, and maintains security solutions, and ensure compliance with relevant policies and regulations. | Senior Level; Responsible for development, implementation and maintenance of cybersecurity infrastructure; Plans, tests, implements, and maintains security solutions, and ensure compliance with relevant policies and regulations. | Senior Level; Responsible for development, implementation and maintenance of cybersecurity infrastructure; Plans, tests, implements, and maintains security solutions, and ensure compliance with relevant policies and regulations. | Senior Level; Responsible for development, implementation and maintenance of cybersecurity infrastructure; Plans, tests, implements, and maintains security solutions, and ensure compliance with relevant policies and regulations. | Senior Level; Responsible for development, implementation and maintenance of cybersecurity infrastructure; Plans, tests, implements, and maintains security solutions, and ensure compliance with relevant policies and regulations. | Senior Level; Responsible for development, implementation and maintenance of cybersecurity infrastructure; Plans, tests, implements, and maintains security solutions, and ensure compliance with relevant policies and regulations. | 275
Cyber Architect Analyst | Junior level; Responsible for designing, building, and maintaining an organization's computer and network security infrastructure. Plans, tests, implements, and maintains security solutions, and ensure compliance with relevant policies and regulations. | Junior level; Responsible for designing, building, and maintaining an organization's computer and network security infrastructure. Plans, tests, implements, and maintains security solutions, and ensure compliance with relevant policies and regulations. | Junior level; Responsible for designing, building, and maintaining an organization's computer and network security infrastructure. Plans, tests, implements, and maintains security solutions, and ensure compliance with relevant policies and regulations. | Junior level; Responsible for designing, building, and maintaining an organization's computer and network security infrastructure. Plans, tests, implements, and maintains security solutions, and ensure compliance with relevant policies and regulations. | Junior level; Responsible for designing, building, and maintaining an organization's computer and network security infrastructure. Plans, tests, implements, and maintains security solutions, and ensure compliance with relevant policies and regulations. | Junior level; Responsible for designing, building, and maintaining an organization's computer and network security infrastructure. Plans, tests, implements, and maintains security solutions, and ensure compliance with relevant policies and regulations. | Junior level; Responsible for designing, building, and maintaining an organization's computer and network security infrastructure. Plans, tests, implements, and maintains security solutions, and ensure compliance with relevant policies and regulations. | 245
Business Lead | Responsible for functional activities, responsibilities, and support related to process, procedure, policy; provide day-to-day oversight throughout design, development, and implementation | Responsible for functional activities, responsibilities, and support related to process, procedure, policy; provide day-to-day oversight throughout design, development, and implementation | Responsible for functional activities, responsibilities, and support related to process, procedure, policy; provide day-to-day oversight throughout design, development, and implementation | Responsible for functional activities, responsibilities, and support related to process, procedure, policy; provide day-to-day oversight throughout design, development, and implementation | Responsible for functional activities, responsibilities, and support related to process, procedure, policy; provide day-to-day oversight throughout design, development, and implementation | Responsible for functional activities, responsibilities, and support related to process, procedure, policy; provide day-to-day oversight throughout design, development, and implementation | Responsible for functional activities, responsibilities, and support related to process, procedure, policy; provide day-to-day oversight throughout design, development, and implementation | 280
Senior Business Analyst | Senior Level; Responsible for functional activities, responsibilities, and support related to process, procedure, policy throughout design, development, and implementation | Senior Level; Responsible for functional activities, responsibilities, and support related to process, procedure, policy throughout design, development, and implementation | Senior Level; Responsible for functional activities, responsibilities, and support related to process, procedure, policy throughout design, development, and implementation | Senior Level; Responsible for functional activities, responsibilities, and support related to process, procedure, policy throughout design, development, and implementation | Senior Level; Responsible for functional activities, responsibilities, and support related to process, procedure, policy throughout design, development, and implementation | Senior Level; Responsible for functional activities, responsibilities, and support related to process, procedure, policy throughout design, development, and implementation | Senior Level; Responsible for functional activities, responsibilities, and support related to process, procedure, policy throughout design, development, and implementation | 255
Business Analyst | Junior Level; Responsible for functional activities, responsibilities, and support related to process, procedure, policy throughout design, development, and implementation | Junior Level; Responsible for functional activities, responsibilities, and support related to process, procedure, policy throughout design, development, and implementation | Junior Level; Responsible for functional activities, responsibilities, and support related to process, procedure, policy throughout design, development, and implementation | Junior Level; Responsible for functional activities, responsibilities, and support related to process, procedure, policy throughout design, development, and implementation | Junior Level; Responsible for functional activities, responsibilities, and support related to process, procedure, policy throughout design, development, and implementation | Junior Level; Responsible for functional activities, responsibilities, and support related to process, procedure, policy throughout design, development, and implementation | Junior Level; Responsible for functional activities, responsibilities, and support related to process, procedure, policy throughout design, development, and implementation | 195
Data Migration Developer Lead | Responsible for activities, responsibilities, and support related to data conversion and migration; provide day-to-day oversight throughout design, development, and implementation | Responsible for activities, responsibilities, and support related to data conversion and migration; provide day-to-day oversight throughout design, development, and implementation | Responsible for activities, responsibilities, and support related to data conversion and migration; provide day-to-day oversight throughout design, development, and implementation | Responsible for activities, responsibilities, and support related to data conversion and migration; provide day-to-day oversight throughout design, development, and implementation | Responsible for activities, responsibilities, and support related to data conversion and migration; provide day-to-day oversight throughout design, development, and implementation | Responsible for activities, responsibilities, and support related to data conversion and migration; provide day-to-day oversight throughout design, development, and implementation | Responsible for activities, responsibilities, and support related to data conversion and migration; provide day-to-day oversight throughout design, development, and implementation | 280
Senior Data Migration Developer | Senior Level; Responsible for activities, responsibilities, and support related to data conversion and migration | Senior Level; Responsible for activities, responsibilities, and support related to data conversion and migration | Senior Level; Responsible for activities, responsibilities, and support related to data conversion and migration | Senior Level; Responsible for activities, responsibilities, and support related to data conversion and migration | Senior Level; Responsible for activities, responsibilities, and support related to data conversion and migration | Senior Level; Responsible for activities, responsibilities, and support related to data conversion and migration | Senior Level; Responsible for activities, responsibilities, and support related to data conversion and migration | 255
Data Migration Developer | Junior Level; Responsible for activities, responsibilities, and support related to data conversion and migration | Junior Level; Responsible for activities, responsibilities, and support related to data conversion and migration | Junior Level; Responsible for activities, responsibilities, and support related to data conversion and migration | Junior Level; Responsible for activities, responsibilities, and support related to data conversion and migration | Junior Level; Responsible for activities, responsibilities, and support related to data conversion and migration | Junior Level; Responsible for activities, responsibilities, and support related to data conversion and migration | Junior Level; Responsible for activities, responsibilities, and support related to data conversion and migration | 195
Software Development Lead | Responsible for activities, responsibilities, and support related to software development; provide day-to-day oversight throughout design, development, and implementation | Responsible for activities, responsibilities, and support related to software development; provide day-to-day oversight throughout design, development, and implementation | Responsible for activities, responsibilities, and support related to software development; provide day-to-day oversight throughout design, development, and implementation | Responsible for activities, responsibilities, and support related to software development; provide day-to-day oversight throughout design, development, and implementation | Responsible for activities, responsibilities, and support related to software development; provide day-to-day oversight throughout design, development, and implementation | Responsible for activities, responsibilities, and support related to software development; provide day-to-day oversight throughout design, development, and implementation | Responsible for activities, responsibilities, and support related to software development; provide day-to-day oversight throughout design, development, and implementation | 185
Senior Software Developer | Senior Level; Responsible for activities, responsibilities, and support related to software development | Senior Level; Responsible for activities, responsibilities, and support related to software development | Senior Level; Responsible for activities, responsibilities, and support related to software development | Senior Level; Responsible for activities, responsibilities, and support related to software development | Senior Level; Responsible for activities, responsibilities, and support related to software development | Senior Level; Responsible for activities, responsibilities, and support related to software development | Senior Level; Responsible for activities, responsibilities, and support related to software development | 155
Software Developer | Junior Level; Responsible for activities, responsibilities, and support related to software development | Junior Level; Responsible for activities, responsibilities, and support related to software development | Junior Level; Responsible for activities, responsibilities, and support related to software development | Junior Level; Responsible for activities, responsibilities, and support related to software development | Junior Level; Responsible for activities, responsibilities, and support related to software development | Junior Level; Responsible for activities, responsibilities, and support related to software development | Junior Level; Responsible for activities, responsibilities, and support related to software development | 125
Testing Lead | Responsible for activities, responsibilities, and support related to system testing; provide day-to-day oversight throughout design, development, and implementation | Responsible for activities, responsibilities, and support related to system testing; provide day-to-day oversight throughout design, development, and implementation | Responsible for activities, responsibilities, and support related to system testing; provide day-to-day oversight throughout design, development, and implementation | Responsible for activities, responsibilities, and support related to system testing; provide day-to-day oversight throughout design, development, and implementation | Responsible for activities, responsibilities, and support related to system testing; provide day-to-day oversight throughout design, development, and implementation | Responsible for activities, responsibilities, and support related to system testing; provide day-to-day oversight throughout design, development, and implementation | Responsible for activities, responsibilities, and support related to system testing; provide day-to-day oversight throughout design, development, and implementation | 255
Senior Tester | Senior Level; Responsible for activities, responsibilities, and support related to system testing; Develop test scripts | Senior Level; Responsible for activities, responsibilities, and support related to system testing; Develop test scripts | Senior Level; Responsible for activities, responsibilities, and support related to system testing; Develop test scripts | Senior Level; Responsible for activities, responsibilities, and support related to system testing; Develop test scripts | Senior Level; Responsible for activities, responsibilities, and support related to system testing; Develop test scripts | Senior Level; Responsible for activities, responsibilities, and support related to system testing; Develop test scripts | Senior Level; Responsible for activities, responsibilities, and support related to system testing; Develop test scripts | 149.85
Testing Analyst | Junior Level; Responsible for activities, responsibilities, and support related to system testing; Develop test scripts | Junior Level; Responsible for activities, responsibilities, and support related to system testing; Develop test scripts | Junior Level; Responsible for activities, responsibilities, and support related to system testing; Develop test scripts | Junior Level; Responsible for activities, responsibilities, and support related to system testing; Develop test scripts | Junior Level; Responsible for activities, responsibilities, and support related to system testing; Develop test scripts | Junior Level; Responsible for activities, responsibilities, and support related to system testing; Develop test scripts | Junior Level; Responsible for activities, responsibilities, and support related to system testing; Develop test scripts | 101.25
Reporting Lead | Responsible for managing and overseeing reporting processes, ensuring accurate and timely reporting | Responsible for managing and overseeing reporting processes, ensuring accurate and timely reporting | Responsible for managing and overseeing reporting processes, ensuring accurate and timely reporting | Responsible for managing and overseeing reporting processes, ensuring accurate and timely reporting | Responsible for managing and overseeing reporting processes, ensuring accurate and timely reporting | Responsible for managing and overseeing reporting processes, ensuring accurate and timely reporting | Responsible for managing and overseeing reporting processes, ensuring accurate and timely reporting | 280
Senior Report Developer | Senior Level; Develops, implements, and maintains reporting solutions | Senior Level; Develops, implements, and maintains reporting solutions | Senior Level; Develops, implements, and maintains reporting solutions | Senior Level; Develops, implements, and maintains reporting solutions | Senior Level; Develops, implements, and maintains reporting solutions | Senior Level; Develops, implements, and maintains reporting solutions | Senior Level; Develops, implements, and maintains reporting solutions | 250
Report Developer | Junior Level; Develops, implements, and maintains reporting solutions | Junior Level; Develops, implements, and maintains reporting solutions | Junior Level; Develops, implements, and maintains reporting solutions | Junior Level; Develops, implements, and maintains reporting solutions | Junior Level; Develops, implements, and maintains reporting solutions | Junior Level; Develops, implements, and maintains reporting solutions | Junior Level; Develops, implements, and maintains reporting solutions | 195
Offshore Senior Developer | Senior Level Offshore Developer; Responsible for activities, responsibilities, and support related to software development and overseeing offshore developers | [6 empty] | 80
Offshore Developer | Offshore Developer; Responsible for activities, responsibilities, and support related to software development | [6 empty] | 55
Offshore Junior Developer | Junior Level Offshore Developer; Responsible for activities, responsibilities, and support related to software development | [6 empty] | 40
0