## Instructions
Complete the Pricing Schedule AHCCCS shall pay the awarded contractor based on the total annual amount in 12 equal monthly increments. Provide the annual cost of requested AI Call Center Integration, including Design, Development & Implementation (DDI) and Maintenance & Operations (M&O). AHCCCS anticipates a six (6) to twelve (12)-month DDI, and a four (4)-year M&O period, with a total contract duration of five (5) years. Enter DDI pricing for contracts years 1, and pricing for M&O years 1.5-5. Provide pricing for the Solution Deliverables and associated Milestone payments. Refer to the AI Call Center Integration deliverables in the Requirements Response Matrix for detailed description of each deliverable. Pricing shall be inclusive of all costs associated with the delivery of the services and includes staff time, travel, mileage, insurance, and administrative cost. No additional fees will be paid by AHCCCS. Provide the staffing rates for extra services (for example, rates for modification hours or change requests).

## Summary
Task Order # YH26-0031
AI Call Center Integration
ATTACHMENT B: PRICING PROPOSAL WORKSHEET
OFFEROR NAME: |  |  | Slalom, Inc.
Total System Cost Summaries
This will be the Total Cost Summaries from each of the Tabs in this spreadsheet
Description | One Time Costs | Year 1 Costs | Year 2 Costs | Year 3 Costs | Year 4 Costs | Year 5 Costs
Solution Costs | 0 | 7200000 | 0 | 0 | 0 | 0
| 0 | 7200000 | 0 | 0 | 0 | 0
5-year Cost of Ownership: | 7200000

## Solution Price
Task Order # YH26-0031
AI Call Center Integration
SOLUTION PRICING
**refer to the timeline in the Task Order for a detailed description of the anticipated activities included in each line item**
Provide a line item for all costs. | Total One Time Cost
Description |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
Planning & Requirements | 0 | 720000 | 0 | 0 | 0 | 0 | 720000
Design & Architecture | 0 | 720000 | 0 | 0 | 0 | 0 | 720000
Build & Configuration | 0 | 1800000 | 0 | 0 | 0 | 0 | 1800000
Testing & Validation | 0 | 1080000 | 0 | 0 | 0 | 0 | 1080000
Pilot & Training | 0 | 1080000 | 0 | 0 | 0 | 0 | 1080000
Full Rollout & Go-Live | 0 | 1080000 | 0 | 0 | 0 | 0 | 1080000
Reporting | 0 | 720000 | 0 | 0 | 0 | 0 | 720000
Maintenance & Operations | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subscription & Licensing (if applicable)** | 0 | 0 | 0 | 0 | 0 | 0 | 0
Hosting (if applicable)** | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Cost: | 0 | 7200000 | 0 | 0 | 0 | 0 | 7200000
Solution Costs shall include all travel. Use the following assumptions for estimating travel:
*For Requirements Section of the Scope of Work: 1-2 trips for each State
*For Development: No travel should be assumed
*For Testing the System: 1 trip should be assumed for each State
*For Implementation of the System: 1-2 trips should be assumed for each State
*For Training: 1-2 trips should be assumed for each State
*The duration should be assumed to be 2-3 days per trip for each State
**Please note that the Software and License costs should include licensing costs for each component of the Solution, which will be hosted in the AHCCCS Azure environment. AHCCCS will host the Solution and retain ownership of the licensing for each component.

## Solution Deliverables
Task Order # YH26-0031
AI Call Center Integration
SOLUTION DELIVERABLES
**Refer to AI Call Center Integration Deliverables for detailed description of each item**
Milestone | Base Price | Recurring Cost (if any) | # of Hours | Proposed Timeline
1. Planning and Requirements | 720000 | 10% of Overall Project Effort | 2880 | April-May 2026
a. Weekly Project Planning/Status Meetings | 144000 | Not applicable | 576 | April-May 2026
b. Develop milestone schedule. (weekly, monthly and quarterly) | 144000 | Not applicable | 576 | April-May 2026
c. Requirements Traceability Matrix | 144000 | Not applicable | 576 | April-May 2026
d. Project Management Plan | 144000 | Not applicable | 576 | April-May 2026
e. Communications Management Plan | 144000 | Not applicable | 576 | April-May 2026
2. Design and Architecture | 720000 | 10% of Overall Project Effort | 2880 | April-May 2026
a. Technical Architecture Detailed Description (DTAP) | 180000 | Not applicable | 720 | April-May 2026
b. Requirements Traceability Matrix | 180000 | Not applicable | 720 | April-May 2026
c. Business Continuity, Cyber Incident Response, & Disaster Recovery Plan (BC/CIR/DR) | 180000 | Not applicable | 720 | April-May 2026
d. Business Design / System Design Document (BD/SDD) | 180000 | Not applicable | 720 | April-May 2026
3. Build and Configuration | 1800000 | 25% of Overall Project Effort | 7200 | May-September 2026
a. System Change Plan | 300000 | Not applicable | 1200 | May-September 2026
b. Data Management Plan | 300000 | Not applicable | 1200 | May-September 2026
c. Environmental Monitoring Plan | 300000 | Not applicable | 1200 | May-September 2026
d. System Maintenance Support Plan (SysMSP) | 300000 | Not applicable | 1200 | May-September 2026
e. System Security & Privacy Plan (SSPP) | 300000 | Not applicable | 1200 | May-September 2026
f. Release Management Plan | 300000 | Not applicable | 1200 | May-September 2026
4. Testing and Validation | 1080000 | 15% of Overall Project Effort | 4320 | 2026-10-01
a. Test Management Plan (TMP) | 216000 | Not applicable | 864 | 2026-10-01
b. Validation of test reporting | 216000 | Not applicable | 864 | 2026-10-01
c. Error reporting and remediation planning for test stages | 216000 | Not applicable | 864 | 2026-10-01
d. Testing acceptance signoff | 216000 | Not applicable | 864 | 2026-10-01
e. Quality Management Plan (QMP) | 216000 | Not applicable | 864 | 2026-10-01
5. Pilot and Training | 1080000 | 15% of Overall Project Effort | 4320 | April-December 2026
a. User Training Plan | 540000 | Not applicable | 2160 | 2026-05-01
b. Training Curriculum | 540000 | Not applicable | 2160 | November-December 2026
6. Full RollOut and Go-Live | 1080000 | 15% of Overall Project Effort | 4320 | November-December 2026
a. Implementation/Roll out plan to include dashboard reporting. | 216000 | Not applicable | 864 | November-December 2026
b. Validation of production reports | 216000 | Not applicable | 864 | November-December 2026
c. Ongoing error reporting | 216000 | Not applicable | 864 | November-December 2026
d. Performance Management Plan | 216000 | Not applicable | 864 | November-December 2026
e. Continuance of Operations Program (COOP) | 216000 | Not applicable | 864 | November-December 2026
7. Optimization and Support | 720000 | 10% of Overall Project Effort | 2880 | December 2026-January 2027
a. Post implementation plan for AHCCCS, Genesys and ServiceNow | 144000 | Not applicable | 576 | December 2026-January 2027
b. Post implementation documentation delivery | 144000 | Not applicable | 576 | December 2026-January 2027
c. Post implementation support/maintenance plan | 144000 | Not applicable | 576 | December 2026-January 2027
d. Error reporting and remediation planning | 144000 | Not applicable | 576 | December 2026-January 2027
e. Transition Plan | 144000 | Not applicable | 576 | December 2026-January 2027

## Staffing Rates
Instructions: Please use the cells shaded in yellow to list all position titles and rates associated with your response. Enter the Hourly Billable Rate per Positions for each Position Title. The Hourly Billable Rate should factor in all costs including applicable purchase, delivery, tax, services, safety, license, travel, per diem, Respondent's staff training, facilities, and other such items necessary to complete all deliverables. The Respondent may include additional roles to accurately represent the various classifications and grades of its personnel.
Table 1: Position Titles and Rates
Position Title | Description | HOURLY Billable Rate Per Position
Example - Analyst | Organizes collected data; analyzes data; assist in developing reports. | 65
Subject Matter Expert (SME) | Various functional and technical experts to facilitate project delivery. | 250
Project Manager | The project manager actively manages project budget and work performed. | 188
Project Management Team Member | The project management team member supports the project manager. | 200
Support Staff (if applicable) | Various functional and technical team members to facilitate project delivery. | 175
0
| NOTE: All positions above are from Slalom's Data Management Services agreement with ADOA. | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0